## Sheet1
	2nd October	3rd October	4th October	5th October	6th October		7th October	8th October	9th October	10th October	11th October		12th October	13th October	14th October	15th October	16th October		17th October	18th October	19th October	20th October	21st October

Project manager	Project management, customer Contact						Project management, customer Contact						Project management, customer Contact						Project management, customer Contact

Project manager & Front end developer	Project start

Project manager & Front end developer	Initial meeting

Front end developer		Research

Front end developer			Content planning

Front end developer					Site outline		Site structure

Front end developer								Style tiles

Front end developer & Copywriter										Text content development

Front end developer													Wireframes

Front end developer														Coding, integration and site build.

Photographer														Photographing Products

Front end developer																			Cross platform and browser testing

Front end developer																						Refinement

Project manager & Front end developer																							LAUNCH